## 01_Master_Piers
No. Pier | Ruas Jalan | Zona | STA / Kode Area | Tipe Pier | Tipe Superstruktur | Kontraktor | Status Pier | Overall Progress (%) | Borepile (Titik) | Pilecap (Titik) | Pier Kolom (Titik) | Pierhead (Titik) | LRB (Titik) | Produksi Box Girder | Erection Box Girder | Steel Box Girder | PCU / PCI Girder | WBS Code | Rencana Mulai (Plan) | Rencana Selesai (Plan) | Aktual Mulai (Actual) | Aktual Selesai (Actual) | Status Deviasi WBS | Nilai Rencana (Rp) | Nilai Shop Dwg (Rp) | Nilai Terprogress (Rp) | Nilai Tertagih (MC) (Rp) | % Realisasi Tertagih | Sisa Belum Tertagih (Rp) | Aktivitas Utama
P.1 | Main Road Awal | Zona 0 | P.1 ~ P.2 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.2 | Main Road Awal | Zona 0 | P.2 ~ P.3 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.3 | Main Road Awal | Zona 0 | P.3 ~ P.4 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.4 | Main Road Awal | Zona 0 | P.4 ~ P.5 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.5 | Main Road Awal | Zona 0 | P.5 ~ P.6 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.6 | Main Road Awal | Zona 0 | P.6 ~ P.7 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.7 | Main Road Awal | Zona 0 | P.7 ~ P.8 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.8 | Main Road Awal | Zona 0 | P.8 ~ P.9 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.9 | Main Road Awal | Zona 0 | P.9 ~ P.10 | Single Pier | PCU | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | N/A (0%) | N/A (0%) | N/A (0%) | Selesai (100%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection PCU
P.10 | Main Road Awal | Zona 0 | P.10 ~ P.10A | Single Pier | PCU | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | N/A (0%) | N/A (0%) | N/A (0%) | Selesai (100%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection PCU
P.10A | Main Road Awal | Zona 0 | P.10A ~ P.11 | Single Pier | PCU | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | N/A (0%) | N/A (0%) | N/A (0%) | Selesai (100%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection PCU
P.11 | Main Road Awal | Zona 0 | P.11 ~ P.12 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.12 | Main Road Awal | Zona 0 | P.12 ~ P.13 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.13 | Main Road Awal | Zona 0 | P.13 ~ P.14 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.14 | Main Road Awal | Zona 0 | P.14 ~ P.15 | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.15 | Main Road Awal | Zona 0 | P.15 ~ P.16.S | Single Pier | Single Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.16.S | Main Road Selatan | Zona 1S | P.16.S ~ P.17.S | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Progress (25%) | 1.Zona 1S.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - PCU
P.17.S | Main Road Selatan | Zona 1S | P.17.S ~ P.18.S | Single Pier | SBG | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Progress (38%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - SBG
P.18.S | Main Road Selatan | Zona 1S | P.18.S ~ P.18A.S | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Progress (25%) | 1.Zona 1S.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - PCU
P.18A.S | Main Road Selatan | Zona 1S | P.18A.S ~ P.19.S | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Progress (25%) | 1.Zona 1S.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - PCU
P.19.S | Main Road Selatan | Zona 1S | P.19.S ~ P.20.S | Single Pier | PCU | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | N/A (0%) | N/A (0%) | N/A (0%) | Selesai (100%) | 1.Zona 1S.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Single Pier - PCU
P.20.S | Main Road Selatan | Zona 1S | P.20.S ~ P.21.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 53705536000 | 53776739200 | 40332554400 | 41846739200 | 77.82% | 0 | Single Pier - Single Box Girder
P.21.S | Main Road Selatan | Zona 1S | P.21.S ~ P.22.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.22.S | Main Road Selatan | Zona 1S | P.22.S ~ P.23.S | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Double Box Girder
P.23.S | Main Road Selatan | Zona 1S | P.23.S ~ P.24.S | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Double Box Girder
P.24.S | Main Road Selatan | Zona 1S | P.24.S ~ P.25.S | Single Pier | Double Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Single Pier - Double Box Girder
P.25.S | Main Road Selatan | Zona 1S | P.25.S ~ P.26.S | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Double Box Girder
P.26.S | Main Road Selatan | Zona 1S | P.26.S ~ P.27.S | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Double Box Girder
P.27.S | Main Road Selatan | Zona 1S | P.27.S ~ P.28.S | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Double Box Girder
P.28.S | Main Road Selatan | Zona 1S | P.28.S ~ P.29.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 12810036000 | 12976889200 | 9732666900 | 7421889200 | 57.19% | 2310777700 | Single Pier - Single Box Girder
P.29.S | Main Road Selatan | Zona 1S | P.29.S ~ P.30.S | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 12810036000 | 12976889200 | 12976889200 | 12976889200 | 100.00% | 0 | Single Pier - Single Box Girder
P.30.S | Main Road Selatan | Zona 1S | P.30.S ~ P.31.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.31.S | Main Road Selatan | Zona 1S | P.31.S ~ P.32.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.32.S | Main Road Selatan | Zona 1S | P.32.S ~ P.33.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 2.00 m - Single Box Girder
P.33.S | Main Road Selatan | Zona 1S | P.33.S ~ P.34.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 2.00 m - Single Box Girder
P.34.S | Main Road Selatan | Zona 1S | P.34.S ~ P.35.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Cantilever 1.50 m - Single Box Girder
P.35.S | Main Road Selatan | Zona 1S | P.35.S ~ P.36.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 2.00 m - Single Box Girder
P.36.S | Main Road Selatan | Zona 1S | P.36.S ~ P.37.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 2.00 m - Single Box Girder
P.37.S | Main Road Selatan | Zona 1S | P.37.S ~ P.38.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 1.50 m - Single Box Girder
P.38.S | Main Road Selatan | Zona 1S | P.38.S ~ P.39.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 1.50 m - Single Box Girder
P.39.S | Main Road Selatan | Zona 1S | P.39.S ~ P.40.S | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Single Pier - Single Box Girder
P.40.S | Main Road Selatan | Zona 1S | P.40.S ~ P.41.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.41.S | Main Road Selatan | Zona 1S | P.41.S ~ P.42.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.42.S | Main Road Selatan | Zona 1S | P.42.S ~ P.43.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.43.S | Main Road Selatan | Zona 1S | P.43.S ~ P.44.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.44.S | Main Road Selatan | Zona 1S | P.44.S ~ P.45.S | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Single Pier - Single Box Girder
P.45.S | Main Road Selatan | Zona 1S | P.45.S ~ P.46.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.46.S | Main Road Selatan | Zona 1S | P.46.S ~ P.47.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.47.S | Main Road Selatan | Zona 1S | P.47.S ~ P.48.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.48.S | Main Road Selatan | Zona 1S | P.48.S ~ P.49.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.49.S | Main Road Selatan | Zona 1S | P.49.S ~ P.50.S | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Single Pier - Single Box Girder
P.50.S | Main Road Selatan | Zona 1S | P.50.S ~ P.51.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.51.S | Main Road Selatan | Zona 1S | P.51.S ~ P.52.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.52.S | Main Road Selatan | Zona 1S | P.52.S ~ P.53.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.53.S | Main Road Selatan | Zona 1S | P.53.S ~ P.54.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.54.S | Main Road Selatan | Zona 1S | P.54.S ~ P.55.S | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Single Pier - Single Box Girder
P.55.S | Main Road Selatan | Zona 1S | P.55.S ~ P.56.S | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Progress (25%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - PCU
P.56.S | Main Road Selatan | Zona 1S | P.56.S ~ P.56A.S | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (12/12 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Progress (38%) | Progress (25%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 23385890000 | 23811220800 | 17858415600 | 11606420800 | 48.74% | 6251994800 | Single Pier - PCU
P.56A.S | Main Road Selatan | Zona 1S | P.56A.S ~ P.57.S | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (12/12 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Progress (38%) | Progress (25%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 23385890000 | 23811220800 | 17858415600 | 11606420800 | 48.74% | 6251994800 | Single Pier - PCU
P.57.S | Main Road Selatan | Zona 1S | P.57.S ~ P.58.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (12/12 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Progress (38%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 23385890000 | 23811220800 | 17858415600 | 11606420800 | 48.74% | 6251994800 | Single Pier - Single Box Girder
P.58.S | Main Road Selatan | Zona 1S | P.58.S ~ P.59.S | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1S.3 (Superstruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Single Pier - Single Box Girder
P.59.S | Main Road Selatan | Zona 1S | P.59.S ~ P.60.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.60.S | Main Road Selatan | Zona 1S | P.60.S ~ P.61.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Single Pier - Single Box Girder
P.61.S | Main Road Selatan | Zona 1S | P.61.S ~ P.62.S | Cantilever 1.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 1.00 m - Single Box Girder
P.62.S | Main Road Selatan | Zona 1S | P.62.S ~ P.63.S | Cantilever 2.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Cantilever 2.50 m - Single Box Girder
P.63.S | Main Road Selatan | Zona 2S | P.63.S ~ P.64.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.64.S | Main Road Selatan | Zona 2S | P.64.S ~ P.65.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.65.S | Main Road Selatan | Zona 2S | P.65.S ~ P.66.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.66.S | Main Road Selatan | Zona 2S | P.66.S ~ P.67.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.50 m - Single Box Girder
P.67.S | Main Road Selatan | Zona 2S | P.67.S ~ P.68.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.50 m - Single Box Girder
P.68.S | Main Road Selatan | Zona 2S | P.68.S ~ P.69.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Cantilever 1.50 m - Single Box Girder
P.69.S | Main Road Selatan | Zona 2S | P.69.S ~ P.70.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.50 m - Single Box Girder
P.70.S | Main Road Selatan | Zona 2S | P.70.S ~ P.71.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.50 m - Single Box Girder
P.71.S | Main Road Selatan | Zona 2S | P.71.S ~ P.72.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.50 m - Single Box Girder
P.72.S | Main Road Selatan | Zona 2S | P.72.S ~ P.73.S | Cantilever 1.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.00 m - Single Box Girder
P.73.S | Main Road Selatan | Zona 2S | P.73.S ~ P.74.S | Cantilever 1.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.00 m - Single Box Girder
P.74.S | Main Road Selatan | Zona 2S | P.74.S ~ P.75.S | Cantilever 1.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.00 m - Single Box Girder
P.75.S | Main Road Selatan | Zona 2S | P.75.S ~ P.76.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Single Pier - Single Box Girder
P.76.S | Main Road Selatan | Zona 2S | P.76.S ~ P.77.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.77.S | Main Road Selatan | Zona 2S | P.77.S ~ P.78.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.78.S | Main Road Selatan | Zona 2S | P.78.S ~ P.79.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.79.S | Main Road Selatan | Zona 2S | P.79.S ~ P.80.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.80.S | Main Road Selatan | Zona 2S | P.80.S ~ P.81.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.81.S | Main Road Selatan | Zona 2S | P.81.S ~ P.82.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.82.S | Main Road Selatan | Zona 2S | P.82.S ~ P.83.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Single Pier - Single Box Girder
P.83.S | Main Road Selatan | Zona 2S | P.83.S ~ P.84.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.84.S | Main Road Selatan | Zona 2S | P.84.S ~ P.85.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.85.S | Main Road Selatan | Zona 2S | P.85.S ~ P.86.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.86.S | Main Road Selatan | Zona 2S | P.86.S ~ P.87.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.87.S | Main Road Selatan | Zona 2S | P.87.S ~ P.88.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.88.S | Main Road Selatan | Zona 2S | P.88.S ~ P.89.S | Cantilever 2.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.50 m - Single Box Girder
P.89.S | Main Road Selatan | Zona 2S | P.89.S ~ P.90.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Cantilever 2.00 m - Single Box Girder
P.90.S | Main Road Selatan | Zona 2S | P.90.S ~ P.91.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.91.S | Main Road Selatan | Zona 2S | P.91.S ~ P.92.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.92.S | Main Road Selatan | Zona 2S | P.92.S ~ P.93.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.93.S | Main Road Selatan | Zona 2S | P.93.S ~ P.94.S | Cantilever 2.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.50 m - Single Box Girder
P.94.S | Main Road Selatan | Zona 2S | P.94.S ~ P.95.S | Cantilever 2.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.50 m - Single Box Girder
P.95.S | Main Road Selatan | Zona 2S | P.95.S ~ P.96.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.96.S | Main Road Selatan | Zona 2S | P.96.S ~ P.97.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Single Pier - Single Box Girder
P.97.S | Main Road Selatan | Zona 2S | P.97.S ~ P.98.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.98.S | Main Road Selatan | Zona 2S | P.98.S ~ P.99.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.99.S | Main Road Selatan | Zona 2S | P.99.S ~ P.100.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.100.S | Main Road Selatan | Zona 2S | P.100.S ~ P.101.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Single Pier - Single Box Girder
P.101.S | Main Road Selatan | Zona 2S | P.101.S ~ P.102.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.102.S | Main Road Selatan | Zona 2S | P.102.S ~ P.103.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.103.S | Main Road Selatan | Zona 2S | P.103.S ~ P.104.S | Cantilever 2.50 m | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Cantilever 2.50 m - Single Box Girder
P.104.S | Main Road Selatan | Zona 2S | P.104.S ~ P.105.S | Cantilever 2.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.50 m - Single Box Girder
P.105.S | Main Road Selatan | Zona 2S | P.105.S ~ P.106.S | Cantilever 2.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.50 m - Single Box Girder
P.106.S | Main Road Selatan | Zona 2S | P.106.S ~ P.107.S | Portal | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (12/12 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/8 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 23385890000 | 23811220800 | 13096171440 | 6388933600 | 26.83% | 6707237840 | Portal - Single Box Girder
P.107.S | Main Road Selatan | Zona 2S | P.107.S ~ P.108.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.108.S | Main Road Selatan | Zona 2S | P.108.S ~ P.109.S | Cantilever 2.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 2.00 m - Single Box Girder
P.109.S | Main Road Selatan | Zona 2S | P.109.S ~ P.110.S | Cantilever 1.00 m | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Cantilever 1.00 m - Single Box Girder
P.110.S | Main Road Selatan | Zona 2S | P.110.S ~ P.111.S | Single Pier | Single Box Girder | PT Girder Indonesia | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.111.S | Main Road Selatan | Zona 2S | P.111.S ~ P.112.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.112.S | Main Road Selatan | Zona 2S | P.112.S ~ P.113.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.113.S | Main Road Selatan | Zona 2S | P.113.S ~ P.114.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.114.S | Main Road Selatan | Zona 2S | P.114.S ~ P.115.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.115.S | Main Road Selatan | Zona 2S | P.115.S ~ P.116.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.116.S | Main Road Selatan | Zona 2S | P.116.S ~ P.117.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.117.S | Main Road Selatan | Zona 3S | P.117.S ~ P.118.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.118.S | Main Road Selatan | Zona 3S | P.118.S ~ P.119.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.119.S | Main Road Selatan | Zona 3S | P.119.S ~ P.120.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.120.S | Main Road Selatan | Zona 3S | P.120.S ~ P.121.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.121.S | Main Road Selatan | Zona 3S | P.121.S ~ P.122.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.122.S | Main Road Selatan | Zona 3S | P.122.S ~ P.123.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.123.S | Main Road Selatan | Zona 3S | P.123.S ~ P.124.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.124.S | Main Road Selatan | Zona 3S | P.124.S ~ P.125.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.125.S | Main Road Selatan | Zona 3S | P.125.S ~ P.126.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.126.S | Main Road Selatan | Zona 3S | P.126.S ~ P.127.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.127.S | Main Road Selatan | Zona 3S | P.127.S ~ P.128.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.128.S | Main Road Selatan | Zona 3S | P.128.S ~ P.129.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.129.S | Main Road Selatan | Zona 3S | P.129.S ~ P.130.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.130.S | Main Road Selatan | Zona 3S | P.130.S ~ P.131.S | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.131.S | Main Road Selatan | Zona 3S | P.131.S ~ P.132.S | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.132.S | Main Road Selatan | Zona 3S | P.132.S ~ P.133.S | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.133.S | Main Road Selatan | Zona 3S | P.133.S ~ P.134.S | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.134.S | Main Road Selatan | Zona 3S | P.134.S ~ P.135.S | Single Pier | SBG | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection SBG
P.135.S | Main Road Selatan | Zona 3S | P.135.S ~ P.136.S | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.136.S | Main Road Selatan | Zona 3S | P.136.S ~ P.137.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.137.S | Main Road Selatan | Zona 3S | P.137.S ~ P.138.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.138.S | Main Road Selatan | Zona 3S | P.138.S ~ P.139.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.139.S | Main Road Selatan | Zona 3S | P.139.S ~ P.140.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.140.S | Main Road Selatan | Zona 3S | P.140.S ~ P.141.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.141.S | Main Road Selatan | Zona 3S | P.141.S ~ P.142.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.142.S | Main Road Selatan | Zona 3S | P.142.S ~ P.143.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.143.S | Main Road Selatan | Zona 3S | P.143.S ~ P.144.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.144.S | Main Road Selatan | Zona 3S | P.144.S ~ P.145.S | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.145.S | Main Road Selatan | Zona 3S | P.145.S ~ P.146.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Single Pier - Single Box Girder
P.146.S | Main Road Selatan | Zona 3S | P.146.S ~ P.147.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Single Pier - Single Box Girder
P.147.S | Main Road Selatan | Zona 3S | P.147.S ~ P.148.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3S.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Single Pier - Single Box Girder
P.148.S | Main Road Selatan | Zona 4S | P.148.S ~ P.149.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.149.S | Main Road Selatan | Zona 4S | P.149.S ~ P.150.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.150.S | Main Road Selatan | Zona 4S | P.150.S ~ P.151.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.151.S | Main Road Selatan | Zona 4S | P.151.S ~ P.152.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.152.S | Main Road Selatan | Zona 4S | P.152.S ~ P.153.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.153.S | Main Road Selatan | Zona 4S | P.153.S ~ P.154.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.154.S | Main Road Selatan | Zona 4S | P.154.S ~ P.155.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.155.S | Main Road Selatan | Zona 4S | P.155.S ~ P.156.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.156.S | Main Road Selatan | Zona 4S | P.156.S ~ P.157.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (10/12 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 23385890000 | 23811220800 | 4762244160 | 3632050000 | 15.25% | 1130194160 | Single Pier - Single Box Girder
P.157.S | Main Road Selatan | Zona 4S | P.157.S ~ P.158.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (10/12 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 23385890000 | 23811220800 | 4762244160 | 3632050000 | 15.25% | 1130194160 | Single Pier - Single Box Girder
P.158.S | Main Road Selatan | Zona 4S | P.158.S ~ P.159.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.159.S | Main Road Selatan | Zona 4S | P.159.S ~ P.160.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.160.S | Main Road Selatan | Zona 4S | P.160.S ~ P.161.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.161.S | Main Road Selatan | Zona 4S | P.161.S ~ P.162.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.162.S | Main Road Selatan | Zona 4S | P.162.S ~ P.163.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.163.S | Main Road Selatan | Zona 4S | P.163.S ~ P.164.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.164.S | Main Road Selatan | Zona 4S | P.164.S ~ P.165.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.165.S | Main Road Selatan | Zona 4S | P.165.S ~ P.166.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.166.S | Main Road Selatan | Zona 4S | P.166.S ~ P.167.S | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.167.S | Main Road Selatan | Zona 4S | P.167.S ~ P.168.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.168.S | Main Road Selatan | Zona 4S | P.168.S ~ P.169.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.169.S | Main Road Selatan | Zona 4S | P.169.S ~ P.170.S | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.170.S | Main Road Selatan | Zona 4S | P.170.S ~ P.171.S | Single Pier | Double Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Double Box Girder
P.171.S | Main Road Selatan | Zona 4S | P.171.S ~ P.172.S | Cantilever 2.50 m | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Cantilever 2.50 m - Double Box Girder
P.172.S | Main Road Selatan | Zona 4S | P.172.S ~ P.173.S | Cantilever 2.50 m | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Cantilever 2.50 m - Double Box Girder
P.173.S | Main Road Selatan | Zona 4S | P.173.S ~ P.174.S | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Double Box Girder
P.174.S | Main Road Selatan | Zona 4S | P.174.S ~ P.175.S | Single Pier | Double Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Double Box Girder
P.175.S | Main Road Selatan | Zona 4S | P.175.S ~ P.176.S | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Double Box Girder
P.176.S | Main Road Selatan | Zona 4S | P.176.S ~ P.177.S | Cantilever 1.50 m | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Cantilever 1.50 m - Single Box Girder
P.177.S | Main Road Selatan | Zona 4S | P.177.S ~ P.178 | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4S.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Single Pier - Single Box Girder
P.15.S | Main Road Utara | Zona 1N | P.15.S ~ P.21.N | Single Pier | Balance Cantilever | Unassigned | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Balance Cantilever
P.21.N | Main Road Utara | Zona 1N | P.21.N ~ P.22.N | Single Pier | Balance Cantilever | Unassigned | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Balance Cantilever
P.22.N | Main Road Utara | Zona 1N | P.22.N ~ P.23.N | Single Pier | Balance Cantilever | Unassigned | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Balance Cantilever
P.23.N | Main Road Utara | Zona 1N | P.23.N ~ P.24.N | Single Pier | Single Box Girder | Unassigned | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.24.N | Main Road Utara | Zona 1N | P.24.N ~ P.25.N | Single Pier | Single Box Girder | Unassigned | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.25.N | Main Road Utara | Zona 1N | P.25.N ~ P.26.N | Single Pier | Single Box Girder | Unassigned | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.26.N | Main Road Utara | Zona 1N | P.26.N ~ P.27.N | Single Pier | Single Box Girder | Unassigned | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.27.N | Main Road Utara | Zona 1N | P.27.N ~ P.28.N | Single Pier | Single Box Girder | Unassigned | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.28.N | Main Road Utara | Zona 1N | P.28.N ~ P.29.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.29.N | Main Road Utara | Zona 1N | P.29.N ~ P.30.N | Single Pier | Double Box Girder | PT Girder Indonesia | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Double Box Girder
P.30.N | Main Road Utara | Zona 1N | P.30.N ~ P.31.N | Single Pier | Double Box Girder | PT Girder Indonesia | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Double Box Girder
P.31.N | Main Road Utara | Zona 1N | P.31.N ~ P.32.N | Single Pier | Double Box Girder | PT Girder Indonesia | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Double Box Girder
P.32.N | Main Road Utara | Zona 1N | P.32.N ~ P.33.N | Single Pier | Double Box Girder | PT Girder Indonesia | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Double Box Girder
P.33.N | Main Road Utara | Zona 1N | P.33.N ~ P.34.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.34.N | Main Road Utara | Zona 1N | P.34.N ~ P.35.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.35.N | Main Road Utara | Zona 1N | P.35.N ~ P.36.N | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.36.N | Main Road Utara | Zona 1N | P.36.N ~ P.37.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.37.N | Main Road Utara | Zona 1N | P.37.N ~ P.38.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.38.N | Main Road Utara | Zona 1N | P.38.N ~ P.39.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.39.N | Main Road Utara | Zona 1N | P.39.N ~ P.40.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.40.N | Main Road Utara | Zona 1N | P.40.N ~ P.41.N | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.41.N | Main Road Utara | Zona 1N | P.41.N ~ P.42.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.42.N | Main Road Utara | Zona 1N | P.42.N ~ P.43.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.43.N | Main Road Utara | Zona 1N | P.43.N ~ P.44.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.44.N | Main Road Utara | Zona 1N | P.44.N ~ P.45.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.45.N | Main Road Utara | Zona 1N | P.45.N ~ P.46.N | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.46.N | Main Road Utara | Zona 1N | P.46.N ~ P.47.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.47.N | Main Road Utara | Zona 1N | P.47.N ~ P.48.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.48.N | Main Road Utara | Zona 1N | P.48.N ~ P.49.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.49.N | Main Road Utara | Zona 1N | P.49.N ~ P.50.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.50.N | Main Road Utara | Zona 1N | P.50.N ~ P.51.N | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.51.N | Main Road Utara | Zona 1N | P.51.N ~ P.52.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.52.N | Main Road Utara | Zona 1N | P.52.N ~ P.53.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.53.N | Main Road Utara | Zona 1N | P.53.N ~ P.54.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.54.N | Main Road Utara | Zona 1N | P.54.N ~ P.55.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.55.N | Main Road Utara | Zona 1N | P.55.N ~ P.56.N | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.56.N | Main Road Utara | Zona 1N | P.56.N ~ P.57.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (12/12 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Progress (38%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 23385890000 | 23811220800 | 17858415600 | 11606420800 | 48.74% | 6251994800 | Erection Single Box Girder
P.57.N | Main Road Utara | Zona 1N | P.57.N ~ P.58.N | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (12/12 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Progress (38%) | Progress (25%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 23385890000 | 23811220800 | 17858415600 | 11606420800 | 48.74% | 6251994800 | Erection PCU
P.58.N | Main Road Utara | Zona 1N | P.58.N ~ P.59.N | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Progress (25%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection PCU
P.59.N | Main Road Utara | Zona 1N | P.59.N ~ P.60.N | Single Pier | PCU | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Progress (25%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection PCU
P.60.N | Main Road Utara | Zona 1N | P.60.N ~ P.61.N | Single Pier | SBG | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (8/8 Terpasang) | N/A (0%) | N/A (0%) | Selesai (100%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection SBG
P.61.N | Main Road Utara | Zona 1N | P.61.N ~ P.62.N | Single Pier | SBG | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Progress (38%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection SBG
P.62.N | Main Road Utara | Zona 1N | P.62.N ~ P.63.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.63.N | Main Road Utara | Zona 1N | P.63.N ~ P.64.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.64.N | Main Road Utara | Zona 1N | P.64.N ~ P.65.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.65.N | Main Road Utara | Zona 1N | P.65.N ~ P.66.N | Single Pier | Single Box Girder | PT Wijaya Karya | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 1N.3 (Superstruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Erection Single Box Girder
P.66.N | Main Road Utara | Zona 1N | P.66.N ~ P.67.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.67.N | Main Road Utara | Zona 1N | P.67.N ~ P.68.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.68.N | Main Road Utara | Zona 1N | P.68.N ~ P.69.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 75 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Progress (67%) | Belum (0/4 Unit) | Selesai (100%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 1N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 7769166900 | 4803889200 | 46.37% | 2965277700 | Erection Single Box Girder
P.69.N | Main Road Utara | Zona 2N | P.69.N ~ P.70.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.70.N | Main Road Utara | Zona 2N | P.70.N ~ P.71.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.71.N | Main Road Utara | Zona 2N | P.71.N ~ P.72.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.72.N | Main Road Utara | Zona 2N | P.72.N ~ P.73.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.73.N | Main Road Utara | Zona 2N | P.73.N ~ P.74.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.74.N | Main Road Utara | Zona 2N | P.74.N ~ P.75.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.75.N | Main Road Utara | Zona 2N | P.75.N ~ P.76.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.76.N | Main Road Utara | Zona 2N | P.76.N ~ P.77.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.77.N | Main Road Utara | Zona 2N | P.77.N ~ P.78.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.78.N | Main Road Utara | Zona 2N | P.78.N ~ P.79.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.79.N | Main Road Utara | Zona 2N | P.79.N ~ P.80.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.80.N | Main Road Utara | Zona 2N | P.80.N ~ P.81.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-05-15 | 2026-06-30 | 2025-05-15 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.81.N | Main Road Utara | Zona 2N | P.81.N ~ P.82.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.82.N | Main Road Utara | Zona 2N | P.82.N ~ P.83.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.83.N | Main Road Utara | Zona 2N | P.83.N ~ P.84.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.84.N | Main Road Utara | Zona 2N | P.84.N ~ P.85.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.85.N | Main Road Utara | Zona 2N | P.85.N ~ P.86.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.86.N | Main Road Utara | Zona 2N | P.86.N ~ P.87.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.87.N | Main Road Utara | Zona 2N | P.87.N ~ P.88.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.88.N | Main Road Utara | Zona 2N | P.88.N ~ P.89.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.89.N | Main Road Utara | Zona 2N | P.89.N ~ P.90.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.90.N | Main Road Utara | Zona 2N | P.90.N ~ P.91.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.91.N | Main Road Utara | Zona 2N | P.91.N ~ P.92.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.92.N | Main Road Utara | Zona 2N | P.92.N ~ P.93.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.93.N | Main Road Utara | Zona 2N | P.93.N ~ P.94.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.94.N | Main Road Utara | Zona 2N | P.94.N ~ P.95.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.95.N | Main Road Utara | Zona 2N | P.95.N ~ P.96.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.96.N | Main Road Utara | Zona 2N | P.96.N ~ P.97.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.97.N | Main Road Utara | Zona 2N | P.97.N ~ P.98.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.98.N | Main Road Utara | Zona 2N | P.98.N ~ P.99.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.99.N | Main Road Utara | Zona 2N | P.99.N ~ P.100.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.100.N | Main Road Utara | Zona 2N | P.100.N ~ P.101.N | Single Pier | PCU | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection PCU
P.101.N | Main Road Utara | Zona 2N | P.101.N ~ P.102.N | Single Pier | SBG | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection SBG
P.102.N | Main Road Utara | Zona 2N | P.102.N ~ P.103.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.103.N | Main Road Utara | Zona 2N | P.103.N ~ P.104.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.104.N | Main Road Utara | Zona 2N | P.104.N ~ P.105.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.105.N | Main Road Utara | Zona 2N | P.105.N ~ P.106.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.106.N | Main Road Utara | Zona 2N | P.106.N ~ P.107.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.107.N | Main Road Utara | Zona 2N | P.107.N ~ P.108.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.108.N | Main Road Utara | Zona 2N | P.108.N ~ P.109.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.109.N | Main Road Utara | Zona 2N | P.109.N ~ P.110.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.110.N | Main Road Utara | Zona 2N | P.110.N ~ P.111.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.111.N | Main Road Utara | Zona 2N | P.111.N ~ P.112.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.112.N | Main Road Utara | Zona 2N | P.112.N ~ P.113.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.113.N | Main Road Utara | Zona 2N | P.113.N ~ P.114.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.114.N | Main Road Utara | Zona 2N | P.114.N ~ P.115.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.115.N | Main Road Utara | Zona 2N | P.115.N ~ P.116.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.116.N | Main Road Utara | Zona 2N | P.116.N ~ P.117.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.117.N | Main Road Utara | Zona 2N | P.117.N ~ P.118.N | Single Pier | PCU | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection PCU
P.118.N | Main Road Utara | Zona 2N | P.118.N ~ P.119.N | Single Pier | PCU | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection PCU
P.119.N | Main Road Utara | Zona 2N | P.119.N ~ P.120.N | Single Pier | PCU | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection PCU
P.120.N | Main Road Utara | Zona 2N | P.120.N ~ P.121.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 25 | Selesai (8/8 Titik Selesai) | Progress (20%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-08-01 | 2026-06-30 | 2025-08-01 | - | Critical | 10307536000 | 10358889200 | 2589722300 | 1290728800 | 12.46% | 1298993500 | Erection Single Box Girder
P.121.N | Main Road Utara | Zona 2N | P.121.N ~ P.122.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.122.N | Main Road Utara | Zona 2N | P.122.N ~ P.123.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 55 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 2/2 (50%)) | Belum (0%) | Belum (0/4 Unit) | Progress (57%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 2N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 5697389060 | 2458751600 | 23.74% | 3238637460 | Erection Single Box Girder
P.123.N | Main Road Utara | Zona 3N | P.123.N ~ P.124.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.124.N | Main Road Utara | Zona 3N | P.124.N ~ P.125.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.125.N | Main Road Utara | Zona 3N | P.125.N ~ P.126.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.126.N | Main Road Utara | Zona 3N | P.126.N ~ P.127.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.127.N | Main Road Utara | Zona 3N | P.127.N ~ P.128.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.128.N | Main Road Utara | Zona 3N | P.128.N ~ P.129.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.129.N | Main Road Utara | Zona 3N | P.129.N ~ P.130.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.130.N | Main Road Utara | Zona 3N | P.130.N ~ P.131.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.131.N | Main Road Utara | Zona 3N | P.131.N ~ P.132.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.132.N | Main Road Utara | Zona 3N | P.132.N ~ P.133.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.133.N | Main Road Utara | Zona 3N | P.133.N ~ P.134.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.134.N | Main Road Utara | Zona 3N | P.134.N ~ P.135.N | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.135.N | Main Road Utara | Zona 3N | P.135.N ~ P.136.N | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.136.N | Main Road Utara | Zona 3N | P.136.N ~ P.137.N | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.137.N | Main Road Utara | Zona 3N | P.137.N ~ P.138.N | Single Pier | SBG | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection SBG
P.138.N | Main Road Utara | Zona 3N | P.138.N ~ P.139.N | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.139.N | Main Road Utara | Zona 3N | P.139.N ~ P.140.N | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.140.N | Main Road Utara | Zona 3N | P.140.N ~ P.141.N | Single Pier | PCU | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection PCU
P.141.N | Main Road Utara | Zona 3N | P.141.N ~ P.142.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.142.N | Main Road Utara | Zona 3N | P.142.N ~ P.143.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.143.N | Main Road Utara | Zona 3N | P.143.N ~ P.144.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.144.N | Main Road Utara | Zona 3N | P.144.N ~ P.145.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.145.N | Main Road Utara | Zona 3N | P.145.N ~ P.146.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.146.N | Main Road Utara | Zona 3N | P.146.N ~ P.147.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.147.N | Main Road Utara | Zona 3N | P.147.N ~ P.148.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.148.N | Main Road Utara | Zona 3N | P.148.N ~ P.149.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.149.N | Main Road Utara | Zona 3N | P.149.N ~ P.150.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.150.N | Main Road Utara | Zona 3N | P.150.N ~ P.151.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.151.N | Main Road Utara | Zona 3N | P.151.N ~ P.152.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.152.N | Main Road Utara | Zona 3N | P.152.N ~ P.153.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 35 | Selesai (8/8 Titik Selesai) | Progress (50%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 3N.2 (Substruktur) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | On Track | 10307536000 | 10358889200 | 3625611220 | 1678536400 | 16.20% | 1947074820 | Erection Single Box Girder
P.153.N | Main Road Utara | Zona 4N | P.153.N ~ P.154.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.154.N | Main Road Utara | Zona 4N | P.154.N ~ P.155.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.155.N | Main Road Utara | Zona 4N | P.155.N ~ P.156.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.156.N | Main Road Utara | Zona 4N | P.156.N ~ P.157.N | Single Pier | Single Box Girder | PT Girder Indonesia | Open | 20 | Progress (10/12 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Critical | 23385890000 | 23811220800 | 4762244160 | 3632050000 | 15.25% | 1130194160 | Erection Single Box Girder
P.157.N | Main Road Utara | Zona 4N | P.157.N ~ P.158.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (10/12 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 23385890000 | 23811220800 | 4762244160 | 3632050000 | 15.25% | 1130194160 | Erection Single Box Girder
P.158.N | Main Road Utara | Zona 4N | P.158.N ~ P.159.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.159.N | Main Road Utara | Zona 4N | P.159.N ~ P.160.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.160.N | Main Road Utara | Zona 4N | P.160.N ~ P.161.N | Single Pier | Single Box Girder | PT Girder Indonesia | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2025-11-01 | 2026-06-30 | 2025-11-01 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.161.N | Main Road Utara | Zona 4N | P.161.N ~ P.162.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.162.N | Main Road Utara | Zona 4N | P.162.N ~ P.163.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.163.N | Main Road Utara | Zona 4N | P.163.N ~ P.164.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.164.N | Main Road Utara | Zona 4N | P.164.N ~ P.165.N | Single Pier | Single Box Girder | PT Girder Indonesia | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.165.N | Main Road Utara | Zona 4N | P.165.N ~ P.166.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.166.N | Main Road Utara | Zona 4N | P.166.N ~ P.167.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.167.N | Main Road Utara | Zona 4N | P.167.N ~ P.168.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.168.N | Main Road Utara | Zona 4N | P.168.N ~ P.169.N | Single Pier | Double Box Girder | PT Girder Indonesia | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.169.N | Main Road Utara | Zona 4N | P.169.N ~ P.170.N | Single Pier | Double Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.170.N | Main Road Utara | Zona 4N | P.170.N ~ P.171.N | Single Pier | Double Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.171.N | Main Road Utara | Zona 4N | P.171.N ~ P.172.N | Single Pier | Double Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.172.N | Main Road Utara | Zona 4N | P.172.N ~ P.173.N | Single Pier | Double Box Girder | PT Girder Indonesia | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.173.N | Main Road Utara | Zona 4N | P.173.N ~ P.174.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.174.N | Main Road Utara | Zona 4N | P.174.N ~ P.175.N | Single Pier | Single Box Girder | PT Girder Indonesia | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.175.N | Main Road Utara | Zona 4N | P.175.N ~ P.176.N | Single Pier | SBG | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection SBG
PT Girder Indonesia" #337 | PT Girder Indonesia" | Zona 0 | - | Single Pier | Box Girder | Unassigned | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2026-01-15 | 2026-06-30 | 2026-01-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Pekerjaan Substruktur
P.176.N | Main Road Utara | Zona 4N | P.176.N ~ P.177.N | Single Pier | SBG | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection SBG
PT Girder Indonesia" #339 | PT Girder Indonesia" | Zona 0 | - | Single Pier | Box Girder | Unassigned | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2026-01-15 | 2026-06-30 | 2026-01-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Pekerjaan Substruktur
P.177.N | Main Road Utara | Zona 4N | P.177.N ~ P.178.N | Single Pier | SBG | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection SBG
PT Girder Indonesia" #341 | PT Girder Indonesia" | Zona 0 | - | Single Pier | Box Girder | Unassigned | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2026-01-15 | 2026-06-30 | 2026-01-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Pekerjaan Substruktur
P.178.N | Main Road Utara | Zona 4N | P.178.N ~ P.179.N | Single Pier | SBG | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection SBG
PT Girder Indonesia" #343 | PT Girder Indonesia" | Zona 0 | - | Single Pier | Box Girder | Unassigned | Closed | 100 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Selesai (Lift Selesai (100%)) | Selesai (100%) | Selesai (4/4 Terpasang) | Selesai (100%) | Selesai (100%) | N/A (0%) | N/A (0%) | 1.Zona 0.3 (Superstruktur) | 2026-01-15 | 2026-06-30 | 2026-01-15 | 2025-12-15 | Ahead | 10307536000 | 10358889200 | 10358889200 | 10358889200 | 100.00% | 0 | Pekerjaan Substruktur
P.179.N | Main Road Utara | Zona 4N | P.179.N ~ P.180.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.180.N | Main Road Utara | Zona 4N | P.180.N ~ P.181.N | Single Pier | Single Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.181.N | Main Road Utara | Zona 4N | P.181.N ~ P.182.N | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.182.N | Main Road Utara | Zona 4N | P.182.N ~ P.178 | Single Pier | Single Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4N.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Single Box Girder
P.178 | Main Road Akhir | Zona 4 Akhir | P.178 ~ P.179 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.179 | Main Road Akhir | Zona 4 Akhir | P.179 ~ P.180 | Single Pier | Double Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.180 | Main Road Akhir | Zona 4 Akhir | P.180 ~ P.181 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.181 | Main Road Akhir | Zona 4 Akhir | P.181 ~ P.182 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.182 | Main Road Akhir | Zona 4 Akhir | P.182 ~ P.183 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.183 | Main Road Akhir | Zona 4 Akhir | P.183 ~ P.184 | Single Pier | Double Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.184 | Main Road Akhir | Zona 4 Akhir | P.184 ~ P.185 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.185 | Main Road Akhir | Zona 4 Akhir | P.185 ~ P.186 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.186 | Main Road Akhir | Zona 4 Akhir | P.186 ~ P.187 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.187 | Main Road Akhir | Zona 4 Akhir | P.187 ~ P.188 | Single Pier | Double Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.188 | Main Road Akhir | Zona 4 Akhir | P.188 ~ P.189 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.189 | Main Road Akhir | Zona 4 Akhir | P.189 ~ P.190 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.190 | Main Road Akhir | Zona 4 Akhir | P.190 ~ P.191 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.191 | Main Road Akhir | Zona 4 Akhir | P.191 ~ P.192 | Single Pier | Double Box Girder | PT Wijaya Karya | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.192 | Main Road Akhir | Zona 4 Akhir | P.192 ~ P.193 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.193 | Main Road Akhir | Zona 4 Akhir | P.193 ~ P.194 | Single Pier | Double Box Girder | PT Wijaya Karya | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.194 | Main Road Akhir | Zona 4 Akhir | P.194 ~ P.195 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.195 | Main Road Akhir | Zona 4 Akhir | P.195 ~ P.196 | Single Pier | Double Box Girder | Unassigned | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.196 | Main Road Akhir | Zona 4 Akhir | P.196 ~ P.197 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.197 | Main Road Akhir | Zona 4 Akhir | P.197 ~ P.198 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.198 | Main Road Akhir | Zona 4 Akhir | P.198 ~ P.199 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.199 | Main Road Akhir | Zona 4 Akhir | P.199 ~ P.200 | Single Pier | Double Box Girder | Unassigned | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.200 | Main Road Akhir | Zona 4 Akhir | P.200 ~ P.201 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.201 | Main Road Akhir | Zona 4 Akhir | P.201 ~ P.202 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.202 | Main Road Akhir | Zona 4 Akhir | P.202 ~ P.203 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.203 | Main Road Akhir | Zona 4 Akhir | P.203 ~ P.204 | Single Pier | Double Box Girder | Unassigned | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.204 | Main Road Akhir | Zona 4 Akhir | P.204 ~ P.205 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.205 | Main Road Akhir | Zona 4 Akhir | P.205 ~ P.206 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.206 | Main Road Akhir | Zona 4 Akhir | P.206 ~ P.207 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.207 | Main Road Akhir | Zona 4 Akhir | P.207 ~ P.208 | Single Pier | Double Box Girder | Unassigned | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.208 | Main Road Akhir | Zona 4 Akhir | P.208 ~ P.209 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.209 | Main Road Akhir | Zona 4 Akhir | P.209 ~ P.210 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.210 | Main Road Akhir | Zona 4 Akhir | P.210 ~ P.211 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.211 | Main Road Akhir | Zona 4 Akhir | P.211 ~ P.212 | Single Pier | Double Box Girder | Unassigned | Open | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Critical | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.212 | Main Road Akhir | Zona 4 Akhir | P.212 ~ P.213 | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
P.213 | Main Road Akhir | Zona 4 Akhir | - | Single Pier | Double Box Girder | Unassigned | On Progress | 20 | Progress (6/8 Titik Pengeboran) | Belum (0%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Belum (0%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.Zona 4 Akhir.1 (Pondasi) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | Delayed | 10307536000 | 10358889200 | 2071777840 | 1097800000 | 10.60% | 973977840 | Erection Double Box Girder
Timbunan | Ramp On RE Martinadata (RMO) | RMO | Timbunan ~ RA.1 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Pekerjaan Substruktur
RA.1 | Ramp On RE Martinadata (RMO) | RMO | RA.1 ~ RMO.1 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RMO.1 | Ramp On RE Martinadata (RMO) | RMO | RMO.1 ~ RMO.2 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
RMO.2 | Ramp On RE Martinadata (RMO) | RMO | RMO.2 ~ RMO.3 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
RMO.3 | Ramp On RE Martinadata (RMO) | RMO | RMO.3 ~ RMO.4 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
RMO.4 | Ramp On RE Martinadata (RMO) | RMO | RMO.4 ~ RMO.5 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
RMO.5 | Ramp On RE Martinadata (RMO) | RMO | RMO.5 ~ RMO.6 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
RMO.6 | Ramp On RE Martinadata (RMO) | RMO | RMO.6 ~ P.1 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RMO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
RAO.1 | Ramp On Ancol Timur (RAO) | RAO | RAO.1 ~ RAO.2 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.2 | Ramp On Ancol Timur (RAO) | RAO | RAO.2 ~ RAO.3 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.3 | Ramp On Ancol Timur (RAO) | RAO | RAO.3 ~ RAO.4 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.4 | Ramp On Ancol Timur (RAO) | RAO | RAO.4 ~ RAO.5 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.5 | Ramp On Ancol Timur (RAO) | RAO | RAO.5 ~ RAO.6 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.6 | Ramp On Ancol Timur (RAO) | RAO | RAO.6 ~ RAO.7 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.7 | Ramp On Ancol Timur (RAO) | RAO | RAO.7 ~ RAO.8 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.8 | Ramp On Ancol Timur (RAO) | RAO | RAO.8 ~ RAO.9 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.9 | Ramp On Ancol Timur (RAO) | RAO | RAO.9 ~ RAO.10 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.10 | Ramp On Ancol Timur (RAO) | RAO | RAO.10 ~ RAO.11 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.11 | Ramp On Ancol Timur (RAO) | RAO | RAO.11 ~ RAO.12 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.12 | Ramp On Ancol Timur (RAO) | RAO | RAO.12 ~ RAO.13 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.13 | Ramp On Ancol Timur (RAO) | RAO | RAO.13 ~ RAO.14 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.14 | Ramp On Ancol Timur (RAO) | RAO | RAO.14 ~ RAO.15 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAO.15 | Ramp On Ancol Timur (RAO) | RAO | RAO.15 ~ RAO.16 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
RAO.16 | Ramp On Ancol Timur (RAO) | RAO | RAO.16 ~ P.22.S | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
P.29.N | Ramp Off Ancol Timur (RAF) | RAF | P.29.N ~ RAF.1 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RAF.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection Single Box Girder
RAF.1 | Ramp Off Ancol Timur (RAF) | RAF | RAF.1 ~ RAF.2 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
RAF.2 | Ramp Off Ancol Timur (RAF) | RAF | RAF.2 ~ RAF.3 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
RAF.3 | Ramp Off Ancol Timur (RAF) | RAF | RAF.3 ~ RAF.4 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
RAF.4 | Ramp Off Ancol Timur (RAF) | RAF | RAF.4 ~ RAF.5 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
RAF.5 | Ramp Off Ancol Timur (RAF) | RAF | RAF.5 ~ RAF.6 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
RAF.6 | Ramp Off Ancol Timur (RAF) | RAF | RAF.6 ~ RAF.7 | Single Pier | Single Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Single Box Girder
RAF.7 | Ramp Off Ancol Timur (RAF) | RAF | RAF.7 ~ RAF.8 | Single Pier | Balance Katilever | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Balance Katilever
RAF.8 | Ramp Off Ancol Timur (RAF) | RAF | RAF.8 ~ RAF.9 | Single Pier | Balance Katilever | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Balance Katilever
RAF.9 | Ramp Off Ancol Timur (RAF) | RAF | RAF.9 ~ RAF.10 | Single Pier | Balance Katilever | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Balance Katilever
RAF.10 | Ramp Off Ancol Timur (RAF) | RAF | RAF.10 ~ RAF.11 | Single Pier | SBG | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/8 Unit) | N/A (0%) | N/A (0%) | Belum (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection SBG
RAF.11 | Ramp Off Ancol Timur (RAF) | RAF | RAF.11 ~ RAF.12 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAF.12 | Ramp Off Ancol Timur (RAF) | RAF | RAF.12 ~ RAF.13 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAF.13 | Ramp Off Ancol Timur (RAF) | RAF | RAF.13 ~ RAF.14 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAF.14 | Ramp Off Ancol Timur (RAF) | RAF | RAF.14 ~ RAF.15 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAF.15 | Ramp Off Ancol Timur (RAF) | RAF | RAF.15 ~ RAF.16 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAF.16 | Ramp Off Ancol Timur (RAF) | RAF | RAF.16 ~ RAF.17 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAF.17 | Ramp Off Ancol Timur (RAF) | RAF | RAF.17 ~ RAF.18 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RAF.18 | Ramp Off Ancol Timur (RAF) | RAF | - | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RAF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
P.176.S | Akses Main Road Selatan-HBR 1 (RSF) | RSF | P.176.S ~ RSF.1 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2026-01-15 | 2026-06-30 | 2026-01-15 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
RSF.1 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.1 ~ RSF.2 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.2 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.2 ~ RSF.3 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.3 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.3 ~ RSF.4 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.4 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.4 ~ RSF.5 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.5 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.5 ~ RSF.6 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.6 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.6 ~ RSF.7 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.7 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.7 ~ RSF.8 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.8 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.8 ~ RSF.9 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.9 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.9 ~ RSF.10 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.10 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.10 ~ RSF.11 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.11 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.11 ~ RSF.12 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.12 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.12 ~ RSF.13 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.13 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.13 ~ RSF.13a | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.13a | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.13a ~ RSF.13b | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.13b | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.13b ~ RSF.13c | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.13c | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.13c ~ RSF.14 | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.14 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.14 ~ RSF.14a | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.14a | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.14a ~ RSF.14b | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.14b | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.14b ~ RSF.15 | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.15 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.15 ~ RSF.15a | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.15a | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.15a ~ RSF.15b | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.15b | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.15b ~ RSF.15c | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.15c | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.15c ~ RSF.15d | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.15d | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.15d ~ RSF.15e | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.15e | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.15e ~ RSF.16 | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.16 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.16 ~ RSF.16a | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.16a | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.16a ~ RSF.16b | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.16b | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.16b ~ RSF.16c | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.16c | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.16c ~ RSF.16d | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.16d | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.16d ~ RSF.16e | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.16e | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.16e ~ RSF.16f | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.16f | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.16f ~ RSF.17 | Single Pier | Tie Beam | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection Tie Beam
RSF.17 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.17 ~ RSF.18 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.18 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.18 ~ RSF.19 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.19 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.19 ~ RSF.20 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.20 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.20 ~ RSF.21 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.21 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.21 ~ RSF.22 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.22 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | RSF.22 ~ RSF.23 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.RSF.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Erection PCU
RSF.23 | Akses Main Road Selatan-HBR 1 (RSF) | RSF | - | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RSF.2 (Substruktur) | 2025-03-01 | 2026-06-30 | 2025-03-01 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
Akses Ramp Off Pengganti HBR1-Selatan (J3F) (Timbunan) | Akses Ramp Off Pengganti HBR1-Selatan (J3F) | J3F | Timbunan | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.J3F.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Pekerjaan Substruktur
RUO.1 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.1 ~ RUO.2 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.2 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.2 ~ RUO.3 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.3 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.3 ~ RUO.4 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.4 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.4 ~ RUO.5 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.5 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.5 ~ RUO.6 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.6 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.6 ~ RUO.7 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.7 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.7 ~ RUO.8 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.8 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.8 ~ RUO.9 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.9 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.9 ~ RUO.10 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.10 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.10 ~ RUO.11 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.11 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.11 ~ RUO.12 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.12 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.12 ~ RUO.13 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.13 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.13 ~ RUO.14 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.14 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.14 ~ RUO.15 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.15 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.15 ~ RUO.16 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.16 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.16 ~ RUO.17 | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
RUO.17 | Akses HBR1 – Main Road Utara (RUO) | RUO | RUO.17 ~ P.173.N | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.RUO.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 9679564000 | 9720750400 | 3888300160 | 1433119600 | 14.74% | 2455180560 | Pekerjaan Substruktur
Ramp On Pengganti HBR1-Utara (J3O) (Timbunan) | Ramp On Pengganti HBR1-Utara (J3O) | J3O | Timbunan | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.J3O.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Pekerjaan Substruktur
GPF.1 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.1 ~ GPF.2 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.2 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.2 ~ GPF.3 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.3 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.3 ~ GPF.4 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.4 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.4 ~ GPF.5 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.5 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.5 ~ GPF.6 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.6 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.6 ~ GPF.7 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.7 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.7 ~ GPF.8 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.8 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.8 ~ GPF.9 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.9 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.9 ~ GPF.10 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.10 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.10 ~ GPF.11 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.11 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.11 ~ GPF.12 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.12 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.12 ~ GPF.13 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
GPF.13 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | GPF.13 ~ APF.1 | Single Pier | PCU | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Erection PCU
APF.1 | Ramp Off Pengganti HBR1-Utara (GPF) | GPF | APF.1 ~ Timbunan | Single Pier | Box Girder | Unassigned | On Progress | 40 | Selesai (8/8 Titik Selesai) | Progress (75%) | Belum (Belum Mulai) | Belum (0%) | Belum (0/4 Unit) | Progress (25%) | Belum (0%) | N/A (0%) | N/A (0%) | 1.GPF.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 4143555680 | 1905765200 | 18.40% | 2237790480 | Pekerjaan Substruktur
Frontage Utara (0+000 – 1+223) | Frontage Utara | FU | 0+000 – 1+223 | Timbunan | Box Girder | Unassigned | On Progress | 50 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 1/2 (25%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.FU.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 5179444600 | 2288072800 | 22.09% | 2891371800 | Struktur Timbunan
Frontage Selatan 1* (0+000 – 0+711) | Frontage Selatan 1* | FS-1 | 0+000 – 0+711 | Timbunan | Box Girder | Unassigned | On Progress | 50 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 1/2 (25%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.FS-1.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 5179444600 | 2288072800 | 22.09% | 2891371800 | Struktur Timbunan
Frontage Selatan 2* (0+000 – 0+330) | Frontage Selatan 2* | FS-2 | 0+000 – 0+330 | Timbunan | Box Girder | Unassigned | On Progress | 50 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 1/2 (25%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.FS-2.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 5179444600 | 2288072800 | 22.09% | 2891371800 | Struktur Timbunan
Frontage Melintang 1* (0+000 – 0+080) | Frontage Melintang 1* | FM-1 | 0+000 – 0+080 | Timbunan | Box Girder | Unassigned | On Progress | 50 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 1/2 (25%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.FM-1.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 5179444600 | 2288072800 | 22.09% | 2891371800 | Struktur Timbunan
Frontage Melintang 2* (0+000 – 0+110) | Frontage Melintang 2* | FM-2 | 0+000 – 0+110 | Timbunan | Box Girder | Unassigned | On Progress | 50 | Selesai (8/8 Titik Selesai) | Selesai (100%) | Progress (Lift 1/2 (25%)) | Belum (0%) | Belum (0/4 Unit) | N/A (0%) | N/A (0%) | N/A (0%) | Belum (0%) | 1.FM-2.2 (Substruktur) | 2025-01-05 | 2026-06-30 | 2025-01-05 | - | On Track | 10307536000 | 10358889200 | 5179444600 | 2288072800 | 22.09% | 2891371800 | Struktur Timbunan

## 02_WBS_Hierarchy
WBS ID | Level | WBS Code | WBS Name | Parent WBS | Section | Zone ID
WBS-1 | 1 | 1.0 | Proyek Jalan Tol Harbour Road II (Elevated) Ruas Ancol Timur - Pluit | - | - | -
WBS-2-MA | 2 | 1.1 | Main Road Awal (P.1 ~ P.15) | WBS-1 | Main Road Awal | -
WBS-2-Z1S | 2 | 1.2 | Sisi Selatan Zona 1 (P.16.S ~ P.62.S) | WBS-1 | Sisi Selatan | Z-1S
WBS-2-Z2S | 2 | 1.3 | Sisi Selatan Zona 2 (P.63.S ~ P.116.S) | WBS-1 | Sisi Selatan | Z-2S
WBS-2-Z3S | 2 | 1.4 | Sisi Selatan Zona 3 (P.117.S ~ P.147.S) | WBS-1 | Sisi Selatan | Z-3S
WBS-2-Z4S | 2 | 1.5 | Sisi Selatan Zona 4 (P.148.S ~ P.177.S) | WBS-1 | Sisi Selatan | Z-4S
WBS-2-Z1N | 2 | 1.6 | Sisi Utara Zona 1 (P.21.N ~ P.68.N) | WBS-1 | Sisi Utara | Z-1N
WBS-2-Z2N | 2 | 1.7 | Sisi Utara Zona 2 (P.69.N ~ P.122.N) | WBS-1 | Sisi Utara | Z-2N
WBS-2-Z3N | 2 | 1.8 | Sisi Utara Zona 3 (P.123.N ~ P.152.N) | WBS-1 | Sisi Utara | Z-3N
WBS-2-Z4N | 2 | 1.9 | Sisi Utara Zona 4 (P.153.N ~ P.182.N) | WBS-1 | Sisi Utara | Z-4N
WBS-2-MAK | 2 | 1.10 | Main Road Akhir (P.178 ~ P.213) | WBS-1 | Main Road Akhir | Z-MAK
WBS-2-RAMP | 2 | 1.11 | Ramp On / Off & Akses Simpang Susun | WBS-1 | Ramp | -
WBS-2-FRONT | 2 | 1.12 | Frontage Road & Jembatan Akses | WBS-1 | Frontage | -
WBS-3-MA-SUB | 3 | 1.1.1 | Pekerjaan Pondasi & Substruktur P.1 - P.15 | WBS-2-MA | - | -
WBS-3-MA-SUP | 3 | 1.1.2 | Pekerjaan Superstruktur Box Girder P.1 - P.15 | WBS-2-MA | - | -
WBS-3-Z1S-PREP | 3 | 1.2.1 | Pekerjaan Persiapan, Utilitas & Traffic Management Zona 1S | WBS-2-Z1S | - | -
WBS-3-Z1S-FND | 3 | 1.2.2 | Pekerjaan Pondasi Bored Pile & Pile Cap Zona 1S | WBS-2-Z1S | - | -
WBS-3-Z1S-SUB | 3 | 1.2.3 | Pekerjaan Struktur Bawah (Pier Column & Pier Head) Zona 1S | WBS-2-Z1S | - | -
WBS-3-Z1S-SUP | 3 | 1.2.4 | Pekerjaan Struktur Atas (Erection Double Box Girder) Zona 1S | WBS-2-Z1S | - | -
WBS-3-Z1S-FIN | 3 | 1.2.5 | Pekerjaan Finishing Deck Slab, Barrier & Expansion Joint | WBS-2-Z1S | - | -
WBS-3-Z2S-FND | 3 | 1.3.1 | Pekerjaan Pondasi Bored Pile D1500 & Pile Cap Zona 2S | WBS-2-Z2S | - | -
WBS-3-Z2S-SUB | 3 | 1.3.2 | Pekerjaan Kolom Pier & Pier Head Zona 2S | WBS-2-Z2S | - | -
WBS-3-Z2S-SUP | 3 | 1.3.3 | Pekerjaan Superstruktur Double Box Girder Zona 2S | WBS-2-Z2S | - | -
WBS-3-Z1N-FND | 3 | 1.6.1 | Pekerjaan Pondasi Bored Pile Zona 1N | WBS-2-Z1N | - | -
WBS-3-Z1N-SUB | 3 | 1.6.2 | Pekerjaan Struktur Kolom & Portal Pier Zona 1N | WBS-2-Z1N | - | -
WBS-3-Z1N-SUP | 3 | 1.6.3 | Pekerjaan Superstruktur Girder Zona 1N | WBS-2-Z1N | - | -
WBS-3-RAMP-RAO | 3 | 1.11.1 | Ramp On Ancol Timur (RAO.1 ~ RAO.16) | WBS-2-RAMP | - | -
WBS-3-RAMP-RAF | 3 | 1.11.2 | Ramp Off Ancol Timur (RAF.1 ~ RAF.18) | WBS-2-RAMP | - | -
WBS-3-RAMP-RSF | 3 | 1.11.3 | Akses Main Road Selatan ke HBR 1 (RSF.1 ~ RSF.23) | WBS-2-RAMP | - | -
WBS-4-P18S-COL | 4 | 1.2.3.1 | Struktur Kolom Pier P.18.S | WBS-3-Z1S-SUB | - | -
WBS-5-P18S-REBAR | 5 | 1.2.3.1.1 | Fabrikasi & Pembesian Kolom Pier P.18.S | WBS-4-P18S-COL | - | -
WBS-5-P18S-FORM | 5 | 1.2.3.1.2 | Pemasangan Bekisting Kolom Pier P.18.S | WBS-4-P18S-COL | - | -
WBS-5-P18S-CAST | 5 | 1.2.3.1.3 | Pengecoran Beton Kolom fc 45 MPa P.18.S | WBS-4-P18S-COL | - | -

## 03_Daily_Progress
Log ID | Tanggal | Pier ID | Kontraktor | Zone | Aktivitas / Uraian | Vol Rencana | Vol Aktual | Satuan | Progres Rencana (%) | Progres Aktual (%) | Manpower (Org) | Peralatan | Catatan Lapangan
DLY-2025-09-15-01 | 2025-09-15 | P18S | WIKA | Z-1S | Pemasangan pembesian rebar D32 layer 2 kolom pier P18S dan inspeksi QC bersama Konsultan Pengawas. | 4.5 | 4.1 | Ton | 2.5 | 2.2 | 18 | Crawler Crane 50T, Bar Bender 32mm | Cuaca cerah, inspeksi disetujui (RFI No. WIKA-QC-182).
DLY-2025-09-15-02 | 2025-09-15 | P57S | GI | Z-2S | Pengecoran Pier Column tahap 1 segmen elevasi +8.500 s/d +14.000. | 45 | 42 | m3 | 3 | 2.8 | 22 | Concrete Pump Truck, Mobile Crane 25T, Internal Vibrator (3 unit) | Slump test rata-rata 12±2 cm, pembuatan benda uji silinder 6 set.
DLY-2025-09-14-01 | 2025-09-14 | P34N | WIKA | Z-1N | Stressing tendon longitudinal nomor T-03 dan T-04 pada pier head P34N. | 6 | 6 | Tendon | 1.8 | 1.5 | 12 | Hydraulic Jack 500T, Grouting Machine | Elongasi aktual memenuhi toleransi ±7% spesifikasi teknik.
DLY-2025-09-13-01 | 2025-09-13 | P19S | WIKA | Z-1S | Ereksi bekisting baja baja peri untuk sisi luar pile cap. | 60 | 58 | m2 | 2 | 1.9 | 14 | Mobile Crane 35T, Scaffolding Heavy Duty | Safety briefing K3 mengenai bahaya bekerja di dekat galian.

## 04_Weekly_Cutoff
Cutoff Date (Jumat) | Week No | Periode | Kontraktor | Rencana Mingguan (%) | Realisasi Mingguan (%) | Deviasi (%) | SPI (Schedule Perf Index) | Evaluasi WCM
2025-08-22 | 34 | 18 Aug - 22 Aug 2025 | WIKA | 64.2 | 61.8 | -2.4 | 0.963 | Tertinggal Minor
2025-08-22 | 34 | 18 Aug - 22 Aug 2025 | GI | 52 | 46.5 | -5.5 | 0.894 | Kritis (Perlu Percepatan)
2025-08-22 | 34 | 18 Aug - 22 Aug 2025 | TOTAL | 58.1 | 54.15 | -3.95 | 0.932 | Tertinggal Minor
2025-08-29 | 35 | 25 Aug - 29 Aug 2025 | WIKA | 66 | 63.1 | -2.9 | 0.956 | Tertinggal Minor
2025-08-29 | 35 | 25 Aug - 29 Aug 2025 | GI | 54.5 | 48 | -6.5 | 0.881 | Kritis (Perlu Percepatan)
2025-08-29 | 35 | 25 Aug - 29 Aug 2025 | TOTAL | 60.25 | 55.55 | -4.7 | 0.922 | Tertinggal Minor
2025-09-05 | 36 | 01 Sep - 05 Sep 2025 | WIKA | 68.1 | 65 | -3.1 | 0.954 | Tertinggal Minor
2025-09-05 | 36 | 01 Sep - 05 Sep 2025 | GI | 57 | 49.8 | -7.2 | 0.874 | Kritis (Perlu Percepatan)
2025-09-05 | 36 | 01 Sep - 05 Sep 2025 | TOTAL | 62.55 | 57.4 | -5.15 | 0.918 | Kritis (Perlu Percepatan)
2025-09-12 | 37 | 08 Sep - 12 Sep 2025 | WIKA | 70.3 | 67.2 | -3.1 | 0.956 | Tertinggal Minor
2025-09-12 | 37 | 08 Sep - 12 Sep 2025 | GI | 59.8 | 51.9 | -7.9 | 0.868 | Kritis (Perlu Percepatan)
2025-09-12 | 37 | 08 Sep - 12 Sep 2025 | TOTAL | 65.05 | 59.55 | -5.5 | 0.915 | Kritis (Perlu Percepatan)

## 05_Monthly_MC
Cutoff Date (Tgl 25) | Periode Bulan | Rencana Bulanan (%) | Realisasi Bulanan (%) | Deviasi Bulanan (%) | Rencana Kumulatif (%) | Realisasi Kumulatif (%) | SPI Kumulatif
2025-05-25 | Mei 2025 | 6.8 | 6.1 | -0.7 | 42.5 | 40.8 | 0.96
2025-06-25 | Juni 2025 | 7.2 | 6.4 | -0.8 | 49.7 | 47.2 | 0.95
2025-07-25 | Juli 2025 | 7.5 | 6.2 | -1.3 | 57.2 | 53.4 | 0.934
2025-08-25 | Agustus 2025 | 7 | 5.6 | -1.4 | 64.2 | 59 | 0.919

## 06_BOQ_Contract
No. Mata Pembayaran | Divisi | Uraian Pekerjaan Spesifikasi Umum Bina Marga | Satuan | Harga Satuan (Rp) | Volume Addendum 4 | Nilai Rencana (Rp) | Realisasi Tertagih (MC) | Status Pembayaran
7.1.(1) | DIV-7 | Pondasi Tiang Bor Beton (Bored Pile) Dia. 1200mm | m | 4250000 | 38500 | 163625000000 | 130900000000 | On Progress
7.1.(2) | DIV-7 | Pondasi Tiang Bor Beton (Bored Pile) Dia. 1500mm | m | 6850000 | 14200 | 97270000000 | 77816000000 | On Progress
7.2.(1) | DIV-7 | Beton Struktur Mutu Tinggi fc 35 MPa (Pile Cap Masif) | m3 | 1950000 | 52400 | 102180000000 | 71526000000 | On Progress
7.2.(2) | DIV-7 | Beton Mutu Tinggi fc 45 MPa (Kolom Pier & Pier Head) | m3 | 2450000 | 34800 | 85260000000 | 51156000000 | On Progress
7.3.(1) | DIV-7 | Baja Tulangan Sirip Ulir BjTS 420B (Rebar D16 s/d D32) | kg | 17200 | 18500000 | 318200000000 | 222740000000 | On Progress
7.4.(1) | DIV-7 | Pengadaan & Erection Box Girder Precast Segmental | Bentang | 7450000000 | 248 | 1847600000000 | 1108560000000 | On Progress
7.4.(2) | DIV-7 | Pengadaan & Erection Steel Box Girder Bentang Khusus Rel KAI | kg | 42000 | 1450000 | 60900000000 | 36540000000 | On Progress
7.5.(1) | DIV-7 | Bantalan Karet Elastomer Lead Rubber Bearing (LRB) | Buah | 85000000 | 1240 | 105400000000 | 63240000000 | On Progress

## 07_Constraints_Log
ID Kendala | Pier No | Kategori | Deskripsi Kendala | Dampak Progres | Target Penyelesaian | Status | PIC / Instansi Terkait
CST-001 | P20S | Utilitas | Interferensi pipa gas tekanan tinggi milik PGN diameter 16 inch di koordinat Bored Pile no. 3 & 4. | Pekerjaan pengeboran dihentikan sementara, keterlambatan 3 minggu pada jalur kritis. | 2025-10-05 | Open | Ir. Hendra (PME WIKA)
CST-002 | P56AS | Lahan | Lahan relokasi gudang eksisting warga belum selesai ganti untung oleh BPN/PPK Lahan. | Manuver crawler crane dan rig bore pile belum dapat masuk ke lokasi. | 2025-10-20 | Open | Bambang S. (PPK Pengadaan Tanah)
CST-003 | P110S | Desain | Revisi gambar kerja (Shop Drawing) Pier Head portal akibat geometri jalan rel ganda di bawahnya. | Pabrikasi bekisting khusus tertunda di workshop. | 2025-09-30 | On Progress | Ahmad Fauzi (Lead Structure Consultant)
CST-004 | P178N | Perijinan | Izin Window Time kerja malam dari Balai Teknik Perkeretaapian (BTP) & KAI DAOP 1. | Pengeboran malam dibatasi maksimal 3 jam per malam. | 2025-09-25 | On Progress | Dedy Kurniawan (HSE & Permit GI)
CST-005 | P18S | Material | Keterlambatan pengiriman rebar ulir D32 KS karena kuota rolling pabrik. | Progress rebar sempat drop 5% dari target mingguan. | 2025-08-28 | Closed | Rian Pratama (Procurement WIKA)

## 08_Issues_Action
ID Issue | Tanggal | Pier No | Kontraktor | Deskripsi Masalah | Akar Masalah (Root Cause) | Tindakan Mitigasi Lapangan | PIC | Target Tanggal | Status
ISS-001 | 2025-08-18 | P20S | WIKA | Casing bore pile bengkok saat menabrak boulder batuan di kedalaman 18m. | Data penyelidikan tanah boring log lama tidak mendeteksi lensa batuan keras. | Mobilisasi rotary rock roller bit dan penggantian segmen casing pipa 12mm. | Surya (Geoteknik Engineer WIKA) | 2025-08-25 | Closed
ISS-002 | 2025-09-02 | P57S | GI | Kerusakan pompa hydraulic crane saat penurunan tulangan sangkar rebar. | Kebocoran seal silinder boom utama akibat beban siklis tinggi. | Support darurat menggunakan mobile crane tandem 80T milik Subkon. | Gatot (Equipment Manager GI) | 2025-09-04 | Closed
ISS-003 | 2025-09-10 | P178N | GI | Limpasan air hujan menggenangi pit galian pile cap karena drainase kota tersumbat. | Saluran inlet gorong-gorong Jl. Lodan tersumbat sedimentasi dan sampah. | Pemasangan 3 unit pompa submersible 6 inch dan dewatering parit darurat. | Kurniawan (Site Manager GI) | 2025-09-18 | On Progress

## 09_Resources
Kategori Sumber Daya | Nama Item / Spesifikasi | Kontraktor / Pemasok | Kebutuhan Rencana | Realisasi / Stok Aktual | Satuan | Status Ketersediaan
Material Utama | Beton Ready-mix fc 45 MPa (Pier Head/Column) | PT WIKA Beton Tbk / Adhimix | 18500 | 2400 | m3 | Aman
Material Utama | Baja Tulangan Ulir BJTS 420B D32 | PT Krakatau Steel Tbk | 3400 | 180 | Ton | Menipis
Material Utama | PC Strand 12.7 mm 7-Wire Uncoated | PT VSL Indonesia | 620 | 95 | Ton | Aman
Material Utama | Beton Ready-mix fc 35 MPa (Bored Pile & Pile Cap) | PT Pionirbeton Industri | 14200 | 650 | m3 | Menipis
Material Utama | Elastomeric Bearing Pad 400x500x72mm | PT Karet Ngagel Surabaya | 320 | 15 | Pcs | Kritis
Alat Berat | Bauer BG 28 Rotary Drilling Rig | WIKA | 4 | 3 | Unit | 75% Siap
Alat Berat | Crawler Crane Sumitomo SCX 1500 (150 Ton) | WIKA | 3 | 3 | Unit | 100% Siap
Alat Berat | Mobile Concrete Pump Truck 42m Boom | GI | 3 | 2 | Unit | 66.7% Siap
Alat Berat | Launching Gantry Box Girder 900T | WIKA | 1 | 1 | Unit | 100% Siap
Alat Berat | Genset Cummins 500 kVA Silent Type | GI | 5 | 5 | Unit | 100% Siap
Tenaga Kerja | Tukang Besi (Rebar Fixer) | WIKA | 24 | 22 | Orang | Kurang
Tenaga Kerja | Tukang Kayu & Bekisting | WIKA | 16 | 15 | Orang | Kurang
Tenaga Kerja | Operator Alat Berat & Rigger | WIKA | 8 | 8 | Orang | Cukup
Tenaga Kerja | Inspector QC & Safety K3 | WIKA | 4 | 4 | Orang | Cukup
Tenaga Kerja | Pekerja Pengecoran (Concreter) | GI | 20 | 18 | Orang | Kurang
Tenaga Kerja | Tukang Besi (Rebar Fixer) | GI | 18 | 16 | Orang | Kurang
Tenaga Kerja | Surveyor & Teknisi Lab | GI | 5 | 5 | Orang | Cukup

## 10_Project_Profile
Parameter Induk Proyek HBR II | Nilai / Keterangan Kontrak | Catatan
Nama Proyek | Proyek Jalan Tol Harbour Road II (Elevated) | Jalan Tol Ancol Timur - Pluit (Elevated Harbour Road II)
Kode Proyek | HBR2-TOLL-2024 | HBR-II-ELEVATED
Panjang Trase Elevated | 8.95 KM | Double Decker & Elevated Viaduct
Jumlah Pier Elevated | 312 Titik Pier | Sisi Selatan & Sisi Utara Trase
Tanggal Mulai Kontrak | 2024-01-15 | Awal Pelaksanaan Fisik
Target Selesai Kontrak | 2026-12-31 | Berdasarkan Addendum 4
Target Selesai Sekarang | 2027-03-31 | Jadwal Kerja Aktif
Pemilik Proyek (Client) | PT Citra Marga Nusaphala Persada Tbk (CMNP) | BUJT Badan Usaha Jalan Tol
Konsultan Supervisi | PT Virama Karya - CEC Joint Venture | Pengawas Independen
Kontraktor Pelaksana | WIKA, GI | WIKA & PT Girder Indonesia
Terakhir Disinkronkan | 24/9/2026, 19.37.56 | 1 File Database Google Sheet Terpadu